## KPI
Country | What_Action_Items | Why | Who_Responsible | When_Due_date | How | Progress
Japan | POT Analysis | POT% is not meeting 100% even though we are on target(over 80%). | Nizam, Hakimi & Hanis | Jan, 2022 | 1. Consistency checking between payment term and actual invoice manually 2. Identify the reason of deviated invoices whether it is due to system related only | In Progress
Japan | DAT(Duplicate Audit Tool) | Duplicate Audit Tool was deployed by global team, so we have to complete a validity check whethe it is applicable to us. | Nadzrin & Syahmi | Jan, 2022 | 1. Held a knowledge sharing session internally among our team members (Dec 2021) 2. Perform parallel run for 2 - 3 months (SAP T-code and DAT BI) (in progress) 3. Decide whether we implement new process or not based on our parallel run | In Progress
Korea | C & B analysis - Relocation fees process alignment |  | Julia | Jan, 2022 | 1. To align with HR team and Payroll team on the process of transportation fares for family visitation | In Progress
Korea | C & B analysis - OT-related costs process alignment |  | Julia | Dec, 2021 | 1. Issue has been aligned with GPO, KR local HR and KR CFO - DONE in Dec. 2021 | Complete
Korea | Revised T&E Thresholds Guide to users in KR12 |  | Julia | Dec, 2021 | 1. Notification email with explanation on changes in amount thresholds to be sent out within Dec. 2021 2. Live session on the changes to be conducted in 6 Jan. 2022 | In Progress
Japan | Finance Core knowledge base |  | Japan team | Dec, 2021 | 1. Drafting all the related Tasks. | In Progress
Japan | VoC project |  | Hakimi & Hanis | Mar, 2022 | 1. Need discussion with Yamazaki-san and other party to solve user's question by end of December 2. Send one VoC survey after providing answers to users by end of January 2022 | In Progress
Japan | Egencia Implementation | Replacement of CWT Travel to Egencia | Japan team | April, 2022 | 1. Go through FAQ Egencia and T&E related document 2. Held a meeting discussion to enhance understanding on Japan Credit Card Process Flow 3. Create a simple 1 PPT slide on comparison of Japan Travel Booking Process via CWT/Egencia 4. Going through all T&E Related documents for any updates and amendment | In Progress
Korea | POT Improvement | %POT is lower than other entities based on the following root causes - Based on vendor Payment methods set up as -J: Invoice baseline date is the invoice issued date instead of Invoice process date by EXELA - Payment cycle as 10th, 25th, and End of Month (3 times per Month) - Immediately payment term vendors are around 50% | Jerry | Mar, 2022 | 1. Analyze the lower %POT of KR12 and prepared the Sensitivity Analysis file (May 2021) 2. Organize the meeting with FRA Korea and TCM task owner in order to increase Payment cycle to improve %POT based on the Sensitivity Analysis (Nov 2021) 3. Contact to Procurement team to change immediately payment term vendor and 17 vendors are selected by Procurement to change (Nov 2021) 4. TCM will process payment run on 20th instead of 25th Jan to analyze %POT impact without the additional Payment cycle (Jan 2022) 5. After January %POT Analysis, if the additional Payment cycle is required, R2P will work with TCM task owner closely in order to prevent any service quality disruption (Feb 2022) | In Progress
Japan | T&E Compliant rate improvement | KPI for T&E Compliance Rate are below 85% | Syahmi & Nadzrin | Jan, 2022 | 1. Design a separate Rejection Analysis to identify main contributor of rejection in Concur (Jun 2021) 2. Build an action plan to achieve KPI target of 85% Compliance rate before end of 2021. (Nov 2021) 3. Create a Newsletter to touch on monthly Top 3 Rejection reason and any other important notification for all Japan Business User (Dec 2021) 4. Create other separate email notification to targeted users regarding specific rejection reason in order to increase effectiveness as a follow up action. (Dec 2021) 5. Conduct a direct session in Jan 2022 with users who committed the rejection reason repeatedly since Aug 2021 (in progress) | In Progress
Japan | Knowledge base chatbot project |  | Nadzrin & Hakimi | Mar, 2022 | 1. Have to discuss further with IT representative by mid of January | In Progress
Japan | Asano-san KT | Since Asano san will be transferred to another department. All the task will be transfer to AGSKL team | Japan team | Mar, 2022 | 1. To expediate KT, KT is currently being held everyday. 2. KT is expected to be completed by end of this year. | In Progress
Japan | Nizam KT | Since Nizam is leaving leave Alcon. All the task will be transfer to Hakimi and Hanis | Japan team | Dec, 2021 | 1. KT consist of 2 part. ServiceNOW and Payment Task 2. Current status: ServiceNOW = Complete; Payment Task = KT is in progress 3. Will send the update to Maeda-san and Hakimi every Friday | In Progress
Korea | Global Travel policy |  | Julia | Jan, 2022 | 1. Translation to be completed upon receiving access to the confidential document form Global team within Dec. 2021 | In Progress
Japan | Global Travel policy |  | Nadzrin & Syahmi | Jan, 2022 | 1. Translation to be completed upon receiving access to the confidential document form Global team within Dec. 2021 | In Progress
Korea | Local Addendum revision |  | Julia | Jan, 2022 | 1. Revision on Local Addendum based on the new thresholds and revised Global policy | In Progress
Japan | Local Addendum revision |  | Nadzrin & Syahmi | Jan, 2022 | 1. Revision on Local Addendum based on the new thresholds and revised Global policy | In Progress
Korea | Appzen Configuration setting |  | Julia | Mar, 2022 | 1. Meeting with GPO on confirmation of congifuration setting chage within Dec. 2021 2. Request the change to Appzen team and apply the new configuration | In Progress
Japan | Appzen Configuration setting |  | Nadzrin & Syahmi | Mar, 2022 | 1. Meeting with GPO on confirmation of congifuration setting chage within Dec. 2021 2. Request the change to Appzen team and apply the new configuration | In Progress
Korea | Update of Concur End User Training & related materials on T&E InSight Page |  | Julia | Dec, 2021 | 1. to remove any parts in the slides that state 'contact Concur helpdesk' -DONE on15 Dec. 2021 | Complete
Japan | Update of Concur End User Training & related materials on T&E InSight Page |  | Nadzrin & Syahmi | Dec, 2021 | Action - Required team to update the excel for training material which required to be updates and provide updates by 21st Dec | In Progress
Japan | Update of Concur Approver Training & related materials on T&E InSight Page |  | Nadzrin & Syahmi | Dec, 2021 | Action - Required team to update the excel for training material which required to be updates by 21st Dec | In Progress
Japan | Downpayment Case Study |  | Syahmi | Dec, 2021 | To update manual on several special case for downpayment occured througout year 2021 | In Progress
Japan | Donation | The task is performed rarely once in year end and new year, thus need to have a clear manual for future new joiner | Syahmi | Jan, 2022 | To update SOP for yearly task donation which is incompletely transfered from Iida-san in March 2021 | In Progress
Japan | Payment | Since Nizam is leaving and Hanis is still new, I have to pro actively be ready for payment backup with Hakimi | Syahmi | Feb, 2022 | To go through payment KT by Nizam with Hanis for payment task to refresh on the opration flow. | In Progress
Korea | Query submission mode change to FNOW guidance to all users in KR |  | Julia | Jan, 2022 | 1. Informing all users of Korea of the new method of query submission via email with translated how-to guide - by end of Dec. 2021 2. Giving consistent guide of the change to users via email and messages whenever contacted -end of Jan. 2022 | In Progress

## status
In Progress
Complete
Not Started
Overdue
On Hold