## KPI
Country | What_Action_Items | Why | Who_Responsible | When_Due_date | How | Progress
Japan | POT Analysis | POT% is not meeting 100% even though we are on target(over 80%). | Syahmi | June, 2022 | 1. Consistency checking between payment term and actual invoice manually (Dec 31, 2021) - completed 2. Identify the reason of deviated invoices whether it is due to system related only (Jan 14, 2022) - completed 3. To deep dive into payment term, eg. average payment term for Japan, payment distribution (Feb 20, 2022) completed 4.toWork with IT etc. to reflect correct POT KPIs on dashboard, after deep-dive to capture what the real non POT invoices are. 5.to clarify with IT on (Immediate due net) & (Pay on 31st), which reflecting due date the same as doc date Ticket raised 6.to collect all late invoice submission data for 2022 and to identify any repetitive user for action to be taken on to be started in Feb 7.to revise Alcon's invoice template format, by adding : -Payment term -Payment due date -Invoice date To start on Marc 8. Suggestion : To encourage / ask business partner to pay with Corporate card if amounts is small to discuss 9.to check on any late posted item after 12pm, and have second proposal if necessary to get approval from TL 10. to arrange early payment for related invoice which could breach POT, only for foreign remittance J-type to get approval from TL | In Progress
Japan | DAT(Duplicate Audit Tool) | Duplicate Audit Tool was deployed by global team, so we have to complete a validity check whethe it is applicable to us. | Nadzrin | Mar, 2022 | 1. Held a knowledge sharing session internally among our team members (Dec 2021) 2. Perform parallel run for 2 - 3 months (SAP T-code and DAT BI) (in progress) 3. Decide whether we implement new process or not based on our parallel run (Jan 17 2022) 4. Have a session from Asano-san to learn from the best practice which was being perform in Novartis. 5. Follow the best practice leant from Asano-san to check all payment run item to detect possible duplicate items | Complete
Korea | C & B analysis - Relocation fees process alignment |  | Julia | Jan, 2022 | 1. To align with HR team and Payroll team on the process of transportation fares for family visitation - to arrange a meeting in Jan. -internal discussion within the team on 20 Jan. 2022 - Discussion result to be sent out to stakeholders by 25 Jan. | Complete
Japan | Finance Core knowledge base |  | Kota & Shahril | Apr, 2022 | 1. Arrange the session and invite all of Japan team members (Feb, 2022) (completed) 2. Drafting all the related Tasks, updaet our process flowchart based on FC (Feb18 , 2022) (completed) 3. Improve our chat bot searchability and completenese for T&E FC standard process (Mar 11, 2022) (Completed) 4. Improve our chat bot searchability and completenese for AP FC standard process (Mar 31, 2022) 5. Improve our chat bot searchability and completenese for Customer Solution FC standard process (Apr15, 2022) | In Progress
Japan | VOC project |  | Hakim, Hanis and Ain | Apr, 2022 | 1. Tracking file (4th week of January) 2. Translating survey and preparing survey for customers by 2nd week of January 2022 3.. Send one VoC survey after providing answers to users by end of January 2022 4. Set Outlook email to no reading the email automatically to prevent overlooked email from Yamazaki's side - completed | Overdue
Japan | Egencia Implementation | Replacement of CWT Travel to Egencia | Nadzrin & Shahril | April, 2022 | 1. Go through FAQ Egencia and T&E related document (Completed) 2. Held a meeting discussion to enhance understanding on Japan Credit Card Process Flow 3. Create a simple 1 PPT slide on comparison of Japan Travel Booking Process via CWT/Egencia ( 4. Going through all T&E Related documents for any updates and amendment | In Progress
Korea | POT Improvement | %POT is lower than other entities based on the following root causes - Based on vendor Payment methods set up as -J: Invoice baseline date is the invoice issued date instead of Invoice process date by EXELA - Payment cycle as 10th, 25th, and End of Month (3 times per Month) - Immediately payment term vendors are around 50% | Jerry | Mar, 2022 | 1. Analyze the lower %POT of KR12 and prepared the Sensitivity Analysis file (May 2021) 2. Organize the meeting with FRA Korea and TCM task owner in order to increase Payment cycle to improve %POT based on the Sensitivity Analysis (Nov 2021) 3. Contact to Procurement team to change immediately payment term vendor and 17 vendors are selected by Procurement to change (Nov 2021) 4. TCM will process payment run on 20th instead of 25th Jan to analyze %POT impact without the additional Payment cycle (Jan 2022) 5. After January %POT Analysis, if the additional Payment cycle is required, R2P will work with TCM task owner closely in order to prevent any service quality disruption (Feb 2022) 6. In Jan, %POT presents above 70% and AP proposed Pay Cycle in Feb as 22nd instead of 25th for figuring out whether 20th Payment day is one time improvement or a significant impact for %POT. Based on %POT data in Feb, AP will further investigate by the sensitivity analysis for achieving Global %POT KPI. 7. In Feb, %POT presents 60% and it seems that Jan %POT is abonormal phenomena. AP suggested to TCM team that Pay cycle in March continue as 21st instead of 25th for attaining the sufficient data. With March data, AP will have a better analysis for the additional Pay cycle decision. | In Progress
Japan | Knowledge base chatbot project |  | Nadzrin, Hakimi, Ain, Hanis | Apr, 2022 | 1. Enhance searchability and user-friendliness 2. Improve user interface - to check redundant items | In Progress
Japan | Asano-san KT | Since Asano san will be transferred to another department. All the task will be transfer to AGSKL team | Kota, Shahril, Hanis & Ain | Mar, 2022 | 1. To expediate KT, KT is currently being held 3-4 times a week. 2. KT is expected to be completed by end of Feb, 2022, followed by hypercare session | In Progress
Korea | Query submission mode change to FNOW guidance to all users in KR |  | Julia | Jan, 2022 | 1. Informing all users of Korea of the new method of query submission via email with translated how-to guide - DONE 17 Dec.2021 2. Giving consistent guide of the change to users via email and messages whenever contacted -end of Jan. 2022 | Complete
Japan | VIM Insight Page-FNOW Link Update | Some users use wrong link to access SNOW. Instead of SNOW prod, they went to SNOW stage | Hakimi | March, 2022 | 1. To check and provide correct links for SNOW in the insight page (Jan 3rd week) done 2. To check FNOW template link (Jan 3rd week) done 3. To check tickets send to wrong FNOW Prod - done | Complete
Japan | KPI T&E update | T&E dashboard has been updated in global tableau platform, but it takes some time to take a snapshot of each KPI graph | Kota | Dec, 2021 | 1. Build a python programming utilizing scraping technique to automatically scrape the dashboard (Jan 14, 2021) 2. Automate copy and paste process of screenshots into deck (Jan 21, 2021) | Complete
Japan | FNOW Breached Ticket Analysis | Old operation is not time-efficient | Hakimi | March, 2022 | 1. To provide simple workflow for breached ticket analysis March, 2021) - Created a master ticket log excel with new layout. Simple instruction is given to extract SNOW data, however the new calculations are inaccurate in terms of ticket number - First KT to Hanis. Overall KPI concept is taught - Currently improving Excel and to write SOP | In Progress
Japan | Paperless Project | Due to Law Concerning Preservation of National Tax Records in Electronic Form, Concur process change will be required. | Shahril & Kota | Mar, 2022 | 1. Appzen current configuration setting revisit (Jan 7, 2022) (completed) 2. Public transporation configuration as a reference point (Jan 7, 2022) (completed) 3. Feasibility study whether Appzen can flag it as medium or low risk if the users attach only credit card statement (Jan 7, 2022) (Completed) 4. Data analysis Line by line was held, waiting for Maeda-san review and approval (complete). 5. Devise Timeline for smooth transition for T&E as well as VIM (complete) 6. Reach out ot heavy users and establish VIM coder community 7. Process change communication & action items | In Progress
Japan | Updating Payment Process Workflow | Outdated information | Hakimi | March, 2022 | 1. To update email templates and add more detailed steps to ease newjoiner Payment step file info is updated with parameters settings and added important points - Email templates are changed to the most updated one - completed - to update Netting payment steps, consolidating with Asano's previous task - completed | Complete
Japan | FNOW CIP | Creating templates, QnA, manuals for users | Japan team | May, 2022 | 1. To create templates for FNOW 2. To create Q&A for FNOW 3. To creata manuals for users, and upload them into Insight Page - We are currently going through FNOW tickets to create templates and QnAs for FNOW - Templates and QnA are kept in one-stop access: OneNote NoteBook, thus enabling assoiates to reply faster to user's inquiry - QA draft for AP SNOW has been prepared and checked by reviewer. - done - Currenlty preparing for QA draft TnE | In Progress
Japan | Local Addendum update (JLT approval) | JLT's one over on manager could be CEO. We need to avoid sending an approval email over to CEO or senior management. | Nadzrin & Ain | March, 2022 | 1. Get an internal process alignment within our team 2. Update our local addendum 3. Approver will be company's president | Complete
Japan | KPI presentation deck simplification & improvement | For KPI's deck, simpler the better. One slide with one strong message. | Shahril & Kota | Apr, 2022 | 1. Have a review session with every responsible team and give a feeback to them 2. Update presentation deck based on our feedback and stakeholder's feedback 3. Establish continuous improvement cycle | Not Started
Japan | KPI session recurring meeting set up |  | Hanis & Ain | Mar, 2022 | 1. Send a recurring meeting request to every participants including Iwafuji-san | Complete
Japan | Team standardization | Drive the team stabilization by task allocation, process understanding and knowledge sharing | Shahril | Mar, 2022 | 1 Task assignation to team members for 1st and 2nd back-up. Update the key person for respective tasks (Complete) 2. KT to be done by end of Jun 2022 | In Progress
Japan | Recognition employee of the month | Recognition culture & Winning spirit establishment | Kota, Shahril & Jerry | Mar, 2022 | 1. Reward the team with Appreciation 2. Spread over positive culture among the team | Not Started
Japan | Team building event | Willingness and happy culture | Kota | Dec, 2022 | 1. Have either online or offline team building event once every quarter 2. AED engagement & schycological safety | Not Started
Japan | First Time Right Concept | Sharing the knowledge to ensure the First-Time-Right concept is to prevent the unnecessary waste of time and resources associated with detecting and correcting errors | Shahril | Dec, 2022
Japan | VIM Insight page updation & enahancement |  | Hanis | Jun, 2022 | 1. Simplify Insight page for VIM to ensure user can obtain required information in a short time (Draft completed) 2. Upgrading/Modify Insight page to become user-friendly platform 3. Implementation paperless project through Q&A and files related | In Progress
Japan & Korea | Excel training |  | Kota | Jun, 2022
Japan & Korea | Automation training |  | Kota | Sep, 2022
Japan & Korea | VBA |  | Kota | Sep, 2022
Japan & Korea | PYTHON |  | Kota | Dec, 2022
Japan & Korea | Winning spirit | To show high work ethics and good environment to colleagues to boost the team's motivation and spirit, thus will improve the performance of each team members and the team as whole. | Nadzrin | Dec, 2022 |  | Not Started
Japan & Korea | FIT Idea |  | Jerry & Shahril
Korea | Appzen Optimization | In a bid to optimize Appzen utility, and drive imporved auto approval rate for KR12, a new configuration setting will be implemented based on Sumi's guidance. | Julia | Mar, 2022 | 1. Have a preliminary meeting with Sumi and Andrea -Done on 24 Feb. 2022 2. Get confirmation and approval from Sumi - 9 Mar. 2022 3. Request the new setting to Appzen team and send the request file to Andrea - to be completed within Mar. 2022 -DONE on 10 March | In Progress
Korea | Anto's request on LA sharing and notice email to all users | To send notice email to all users in KR on hard copy submission and share LA with APAC regional leaders | Julia | Mar, 2022 | 1. Get the list of approvers for KR12 associates and share the LA with APAC regional leaders - Done on 1 Mar. 2. Send notice email to all users on hard copy submission -Done on 24 Feb | In Progress
Korea | New Accrual Automation Familiarization | To get used to the new process | Julia | Mar, 2022 | 1. To get used to the new Accrual process and tasks | In Progress
Japan & Korea | Inspire our team to See Brilliantly! | As part of Alcon's 2022 Priorities to Inspire Our People | Abu Zar | Apr, 2022 | 1. To feed team members news on current issue focusing Korea and Japan or Global covering topics on Politics, Economy, Medical/Healthcare, etc. 2. Will send via email on weekly basis. 3. Issue No.1 sent out on Wed,9/3/2022, Issue No.2 sent out on Wed,16/3/2022 | In Progress
Korea | Six Sigma White Belt Certified | By increasing the quality of processes, will improved service, will have more satisfied stakeholders | Abu Zar | Dec, 2022 | 1. To liase with AGS KL Training Manager on the course availability 2. Ms.Logappriya informed there are some upgrades happening to the modules and still waiting for more news on when it will be conducted | Not Started
Korea | The removal AFCM T&E 01.12.15 Review of Overdue Crdit Card Statements | Alcon Korea implemented the Corporate Card payment from IBIP to CBCP June 2021 onwards by Concur implementation. According to this, all Alcon Korea emplyoee Corporate Card expense has been paid to CITI regardless Alcon Korea employees submit ER or not. | Jerry | Feb, 2022 | 1. Through the removal of AFCM T&E.01.12.15Review of Overdue Credit Card Statements control, AP agent will save not only AFCM control process time but also the supporting document preparation time such as Confirmation mail reply from CITI, Document preparation for Line Manager's approval. And Line Manger can save review and approval time | Complete
Japan | BSR reconciliation & knowledge sharing | To prepare material for CFO review & close knowledge gap with team members | Syahmi | Mar, 2022 | 1. Prepare BSR analysis file & update template by Nakamura-san (completed) 2. Prepare CFO BS review file & update template by Okamoto-san (completed) 3.Knowledge sharing with team members | In Progress
Japan | New Accrual Automation Familiarization | To get used to the new process | Syahmi | Mar, 2022 | 1. To get used to the new monthly Accrual process 2. Knowledge sharing with Nadzrin & Ain | In Progress
Japan | Withholding tax overall task consolidation | Withholding tax involves a wide process flow, originally handled by Iida-san & Asano-san, now will be 100% transfered to AGSKL team. Everyone must have the same understanding on what is being processed by the team. | Syahmi | May, 2022 | 1. To get use with withholding tax - VIM application process (Completed) 2. To have KT with Shahril Hanis Ain about ongoing KT by Asano-san, merge all the available task to get better picture on whole process (Pending for Tomeisei Guidelines) 3. Knowledge sharing with teammates | In Progress
Japan | Insight Improvement (Concur) | To become more friendly-user | Ain | June, 2022 | 1. Modify the interface of Concur page to become simpler (Draft completed) 2. Remove duplicate materials 3. Get feedback from user 4. Upload updated information/materials for end user | In Progress
Korea | Deviation approval process improvment | approval eamil to replace the deviation form for cash usage and 60 days ++ items (approval flow line manager->CFO) | Julia | Mar, 2022 | 1. Get alignment with CFO Anto and Ai Kim for improved process for cash usage and claim of 60 days ++ items ERs of users- DONE on 16 March 2. Get confirmation with Ai Kim - to be done by 17 March 3. Send out notification email on changes to all users by 24 March | In Progress
Korea | LA updates to reflect travel booking specifics | LA to include some country specifics for travel bookings via Egencia | Julia | Mar, 2022 | 1. To attend the procurement training on 17 March 2. To update LA to reflect some booking specifics via Egencia - to be done by 24 March 3. To have confirmation with Anto and Ai Kim by end of March | In Progress
Korea | To provide list of users with overdue items unsubmitted to Anto | To monitor overdue unsubmitted items (60 90 days ++) | Julia | Apr, 2022 | 1. To send data to Anto after March 2022 | In Progress
Japan | To report Attchment error in Appzen for 7 reports in FEB | Attachment is not detected in Appzen eventhough User has already attached the receipt in Concur | Nadzrin | Mar, 2022 | 1. To send data to Appzen Supportdesk and ask clarification | In Progress

## status
In Progress
Complete
Not Started
Overdue
On Hold

## completed
Country | What_Action_Items | Why | Who_Responsible | When_Due_date | How | Progress |  | # of completion
Japan | POT Analysis | POT% is not meeting 100% even though we are on target(over 80%). | Syahmi, Hakimi & Hanis | Jan, 2022 | 1. Consistency checking between payment term and actual invoice manually (Dec 31, 2021) - completed 2. Identify the reason of deviated invoices whether it is due to system related only (Jan 14, 2022) - completed 3. To deep dive into payment term, eg. average payment term for Japan, payment distribution (Feb 20, 2022) completed | Complete | Shahril
Japan | DAT(Duplicate Audit Tool) | Duplicate Audit Tool was deployed by global team, so we have to complete a validity check whethe it is applicable to us. | Nadzrin & Syahmi | Jan, 2022 | 1. Held a knowledge sharing session internally among our team members (Dec 2021) 2. Perform parallel run for 2 - 3 months (SAP T-code and DAT BI) (in progress) 3. Decide whether we implement new process or not based on our parallel run (Jan 17 2022) | Complete | Syahmi | 12
Korea | C & B analysis - OT-related costs process alignment |  | Julia | Dec, 2021 | 1. Issue has been aligned with GPO, KR local HR and KR CFO - DONE in Dec. 2021 | Complete | Nadzrin | 8
Korea | Revised T&E Thresholds Guide to users in KR12 |  | Julia | Dec, 2021 | 1. Notification email with explanation on changes in amount thresholds to be sent out within Dec. 2021-DONE 17 Dec. 2021 2. Live session on the changes to be conducted in 6 Jan. 2022-DONE | Complete | Hakimi | 1
Japan | T&E Compliant rate improvement | KPI for T&E Compliance Rate are below 85% | Syahmi & Nadzrin | Jan, 2022 | 1. Design a separate Rejection Analysis to identify main contributor of rejection in Concur (Done on Jun 2021) 2. Build an action plan to achieve KPI target of 85% Compliance rate before end of 2021. (Done on Nov 2021) 3. Create a Newsletter to touch on monthly Top 3 Rejection reason and any other important notification for all Japan Business User (Done on Dec 2021) 4. Create other separate email notification to targeted users regarding specific rejection reason in order to increase effectiveness as a follow up action. (Done on Dec 2021) 5. Conduct a direct session in Jan 2022 with users who committed the rejection reason repeatedly since Aug 2021 (invitation will be sent by 14 Jan 2021, session by 21 Jan 2021) | Complete | Hanis | 1
Korea | Global Travel policy |  | Julia | Jan, 2022 | 1. Translation to be completed upon receiving access to the confidential document form Global team within Dec. 2021- to be completed by 23 Dec. 202-DONE | Complete | Ain
Japan | Global Travel policy |  | Nadzrin & Syahmi | Jan, 2022 | 1. Translation to be completed upon receiving access to the confidential document form Global team within Dec. 2021 | Complete | Jerry
Korea | Local Addendum revision |  | Julia | Jan, 2022 | 1. Revision on Local Addendum based on the new thresholds and revised Global policy - to be completed by 23 Dec. 2021-DONE | Complete | Julia | 6
Japan | Local Addendum revision |  | Nadzrin & Syahmi | Jan, 2022 | 1. Revision on Local Addendum based on the new thresholds and revised Global policy by 24 Dec 2021 | Complete | Abu Zar
Korea | Appzen Configuration setting |  | Julia | Mar, 2022 | 1. Meeting with GPO on confirmation of congifuration setting chage within Dec. 2021-DONE on 21 Dec. 2021 2. Request the change to Appzen team and apply the new configuration - by end of Dec. 2021-DONE on 6 Jan. 2022 -DONE | Complete | Kota | 2
Japan | Appzen Configuration setting |  | Nadzrin & Syahmi | Mar, 2022 | 1. Meeting with other APAC Conutries to standardize the Appzen Configuration Setting for Gift expense type | Complete
Korea | Update of Concur End User Training & related materials on T&E InSight Page |  | Julia | Dec, 2021 | 1. to remove any parts in the slides that state 'contact Concur helpdesk' -DONE on15 Dec. 2021 | Complete
Japan | Update of Concur End User Training & related materials on T&E InSight Page |  | Nadzrin & Syahmi | Dec, 2021 | Action - Required team to update the excel for training material which required to be updates and provide updates by 21st Dec | Complete
Japan | Downpayment Case Study |  | Syahmi | Dec, 2021 | To update manual on several special case for downpayment occured througout year 2021 (27th Dec) | Complete
Japan | Donation | The task is performed rarely once in year end and new year, thus need to have a clear manual for future new joiner | Syahmi | Jan, 2022 | 1. To update SOP for yearly task donation which is incompletely transfered from Iida-san in March 2021 (Feb 10 2022) | Complete
Japan | Payment | Since Nizam is leaving and Hanis is still new, I have to pro actively be ready for payment backup with Hakimi | Syahmi | Jan, 2022 | 1. To go through payment KT by Nizam with Hanis for payment task to refresh on the operation flow Update 3rd Jan : KT is halfway done due to limited time to join the session in the hustle of year end closing. Will continue with Hakimi | Complete
Japan | Year End Schedule update | Global and Japan WD calendar is not aligned for the year end closing. | Kota | Dec, 2021 | 1. To check year end closing calendar updated by Syahmi and identify critical items along with due dates (Dec 22, 2021) 2. Arrange the quick session to explain year end closing calenders along with action items (Dec 23, 2021) | Complete
Japan | 2022 Payment calendar | Payment calendar has not yet been created before, so the approvers have to handle payment approveal on ad-hoc basis. | Kota | Dec, 2021 | 1. To check 2022 payment calendar updated by Nizam and identify if there is any discrepancy between payment run date and our assumption (Dec 22, 2021) 2. Arrange the quick session to explain 2022 payment calendar (Dec 23, 2021) | Complete
Japan | Duplicate Audit Tools | As an alternative way to double confirm current practice / to replace current practice which consume much time | Syahmi and Nadzrin | Dec, 2021 | 1. Knowledge sharing on new DAT with team | Complete
Japan | Automated Posting : T&E accrual Global Enhancement | The system to go live on Jannuary 2022 | Syahmi and Nadzrin | Dec, 2021 | 1. Knowledge sharing on new project of Automated Posting : T&E accrual Global Enhancement | Complete