## KPI
Country | What_Action_Items | Why | Who_Responsible | When_Due_date | How | Progress
Japan | POT Analysis | POT% is not meeting 100% even though we are on target(over 80%). | Nizam, Hakimi & Hanis | Jan, 2022 | 1. Consistency checking between payment term and actual invoice manually (Dec 31, 2021) 2. Identify the reason of deviated invoices whether it is due to system related only (Jan 14, 2022) | In Progress
Japan | DAT(Duplicate Audit Tool) | Duplicate Audit Tool was deployed by global team, so we have to complete a validity check whethe it is applicable to us. | Nadzrin & Syahmi | Jan, 2022 | 1. Held a knowledge sharing session internally among our team members (Dec 2021) 2. Perform parallel run for 2 - 3 months (SAP T-code and DAT BI) (in progress) 3. Decide whether we implement new process or not based on our parallel run | In Progress
Korea | C & B analysis - Relocation fees process alignment |  | Julia | Jan, 2022 | 1. To align with HR team and Payroll team on the process of transportation fares for family visitation - to arrange a meeting in Jan. | In Progress
Korea | C & B analysis - OT-related costs process alignment |  | Julia | Dec, 2021 | 1. Issue has been aligned with GPO, KR local HR and KR CFO - DONE in Dec. 2021 | Complete
Korea | Revised T&E Thresholds Guide to users in KR12 |  | Julia | Dec, 2021 | 1. Notification email with explanation on changes in amount thresholds to be sent out within Dec. 2021-DONE 17 Dec. 2021 2. Live session on the changes to be conducted in 6 Jan. 2022 | In Progress
Japan | Finance Core knowledge base |  | Japan team | Dec, 2021 | 1. Drafting all the related Tasks. | In Progress
Japan | VoC project |  | Hakimi & Hanis | Mar, 2022 | 1. IT team reverted to FRA team. Discuss with Nicholas, Nicholas to deliver feedback 2. Translating survey and preparing survey for customers by 2nd week of January 2022 3.. Send one VoC survey after providing answers to users by end of January 2022 4. To understand Yamasaki's task to prevent invoices from being neglected by end of December | In Progress
Japan | Egencia Implementation | Replacement of CWT Travel to Egencia | Japan team | April, 2022 | 1. Go through FAQ Egencia and T&E related document 2. Held a meeting discussion to enhance understanding on Japan Credit Card Process Flow 3. Create a simple 1 PPT slide on comparison of Japan Travel Booking Process via CWT/Egencia 4. Going through all T&E Related documents for any updates and amendment | In Progress
Korea | POT Improvement | %POT is lower than other entities based on the following root causes - Based on vendor Payment methods set up as -J: Invoice baseline date is the invoice issued date instead of Invoice process date by EXELA - Payment cycle as 10th, 25th, and End of Month (3 times per Month) - Immediately payment term vendors are around 50% | Jerry | Mar, 2022 | 1. Analyze the lower %POT of KR12 and prepared the Sensitivity Analysis file (May 2021) 2. Organize the meeting with FRA Korea and TCM task owner in order to increase Payment cycle to improve %POT based on the Sensitivity Analysis (Nov 2021) 3. Contact to Procurement team to change immediately payment term vendor and 17 vendors are selected by Procurement to change (Nov 2021) 4. TCM will process payment run on 20th instead of 25th Jan to analyze %POT impact without the additional Payment cycle (Jan 2022) 5. After January %POT Analysis, if the additional Payment cycle is required, R2P will work with TCM task owner closely in order to prevent any service quality disruption (Feb 2022) | In Progress
Japan | T&E Compliant rate improvement | KPI for T&E Compliance Rate are below 85% | Syahmi & Nadzrin | Jan, 2022 | 1. Design a separate Rejection Analysis to identify main contributor of rejection in Concur (Done on Jun 2021) 2. Build an action plan to achieve KPI target of 85% Compliance rate before end of 2021. (Done on Nov 2021) 3. Create a Newsletter to touch on monthly Top 3 Rejection reason and any other important notification for all Japan Business User (Done on Dec 2021) 4. Create other separate email notification to targeted users regarding specific rejection reason in order to increase effectiveness as a follow up action. (Done on Dec 2021) 5. Conduct a direct session in Jan 2022 with users who committed the rejection reason repeatedly since Aug 2021 (invitation will be sent by 14 Jan 2021, session by 21 Jan 2021) | In Progress
Japan | Knowledge base chatbot project |  | Nadzrin & Hakimi | Mar, 2022 | 1. Have to discuss further with IT representative by mid of January | In Progress
Japan | Asano-san KT | Since Asano san will be transferred to another department. All the task will be transfer to AGSKL team | Japan team | Mar, 2022 | 1. To expediate KT, KT is currently being held everyday. 2. KT is expected to be completed by end of this year. | In Progress
Japan | Nizam KT | Since Nizam is leaving leave Alcon. All the task will be transfer to Hakimi and Hanis | Japan team | Dec, 2021 | 1. KT consist of 2 part. ServiceNOW and Payment Task 2. Current status: ServiceNOW = Complete; Payment Task = KT is in progress 3. Will send the update to Maeda-san and Hakimi every Friday | In Progress
Korea | Global Travel policy |  | Julia | Jan, 2022 | 1. Translation to be completed upon receiving access to the confidential document form Global team within Dec. 2021- to be completed by 23 Dec. 2021 | In Progress
Japan | Global Travel policy |  | Nadzrin & Syahmi | Jan, 2022 | 1. Translation to be completed upon receiving access to the confidential document form Global team within Dec. 2021 | In Progress
Korea | Local Addendum revision |  | Julia | Jan, 2022 | 1. Revision on Local Addendum based on the new thresholds and revised Global policy - to be completed by 23 Dec. 2021 | In Progress
Japan | Local Addendum revision |  | Nadzrin & Syahmi | Jan, 2022 | 1. Revision on Local Addendum based on the new thresholds and revised Global policy by 24 Dec 2021 | In Progress
Korea | Appzen Configuration setting |  | Julia | Mar, 2022 | 1. Meeting with GPO on confirmation of congifuration setting chage within Dec. 2021-DONE on 21 Dec. 2021 2. Request the change to Appzen team and apply the new configuration - by end of Dec. 2021 | In Progress
Japan | Appzen Configuration setting |  | Nadzrin & Syahmi | Mar, 2022 | 1. Meeting with GPO on confirmation of congifuration setting chage within Dec. 2021 2. Request the change to Appzen team and apply the new configuration | In Progress
Korea | Update of Concur End User Training & related materials on T&E InSight Page |  | Julia | Dec, 2021 | 1. to remove any parts in the slides that state 'contact Concur helpdesk' -DONE on15 Dec. 2021 | Complete
Japan | Update of Concur End User Training & related materials on T&E InSight Page |  | Nadzrin & Syahmi | Dec, 2021 | Action - Required team to update the excel for training material which required to be updates and provide updates by 21st Dec | Complete
Japan | Downpayment Case Study |  | Syahmi | Dec, 2021 | To update manual on several special case for downpayment occured througout year 2021 (In progress) | In Progress
Japan | Donation | The task is performed rarely once in year end and new year, thus need to have a clear manual for future new joiner | Syahmi | Jan, 2022 | 1. To update SOP for yearly task donation which is incompletely transfered from Iida-san in March 2021 (end of Dec) | In Progress
Japan | Payment | Since Nizam is leaving and Hanis is still new, I have to pro actively be ready for payment backup with Hakimi | Syahmi | Dec, 2022 | 1. To go through payment KT by Nizam with Hanis for payment task to refresh on the opration flow (end of Dec) | In Progress
Korea | Query submission mode change to FNOW guidance to all users in KR |  | Julia | Jan, 2022 | 1. Informing all users of Korea of the new method of query submission via email with translated how-to guide - DONE 17 Dec.2021 2. Giving consistent guide of the change to users via email and messages whenever contacted -end of Jan. 2022 | In Progress
Japan | VIM Insight Page-FNOW Link Update | Some users use wrong link to access SNOW. Instead of SNOW prod, they went to SNOW stage | Hakimi | Jan, 2022 | 1. To check and provide correct links for SNOW in the insight page (Jan 1st week) 2. To check FNOW template link (Jan 1st week) | On Hold
Japan | Year End Schedule update | Global and Japan WD calendar is not aligned for the year end closing. | Kota | Dec, 2021 | 1. To check year end closing calendar updated by Syahmi and identify critical items along with due dates (Dec 22, 2021) 2. Arrange the quick session to explain year end closing calenders along with action items (Dec 23, 2021) | Complete
Japan | 2022 Payment calendar | Payment calendar has not yet been created before, so the approvers have to handle payment approveal on ad-hoc basis. | Kota | Dec, 2021 | 1. To check 2022 payment calendar updated by Nizam and identify if there is any discrepancy between payment run date and our assumption (Dec 22, 2021) 2. Arrange the quick session to explain 2022 payment calendar (Dec 23, 2021) | Complete
Japan | KPI T&E update | T&E dashboard has been updated in global tableau platform, but it takes some time to take a snapshot of each KPI graph | Kota | Dec, 2021 | 1. Build a python programming utilizing scraping technique to automatically scrape the dashboard (Dec 23, 2021) 2. Automate copy and paste process of screenshots into deck (Dec 23, 2021) | Overdue
| FNOW Breached Ticket Analysis |  | Hakimi | Feb, 2022 | 1. To provide simple workflow for breached ticket analysis Feb 25, 2021) | On Hold
Japan | Duplicate Audit Tools | As an alternative way to double confirm current practice / to replace current practice which consume much time | Syahmi and Nadzrin | Dec, 2021 | 1. Knowledge sharing on new DAT with team | Complete
Japan | Automated Posting : T&E accrual Global Enhancement | The system to go live on Jannuary 2022 | Syahmi and Nadzrin | Dec, 2021 | 1. Knowledge sharing on new project of Automated Posting : T&E accrual Global Enhancement | Complete
Japan | Hiring status | Replecement of Aiqi and Nizam | Kota | Jan, 2022 | Sharil (replacement of Aiqi) will be joining us on Feb3, 2022. He will be signing our job offer letter. Nurulain(replacement of Nizam) will be joining us on Jan 4th, 2022. Job offer letter will be signed off by her after HR manager e-signs it. | In Progress
Japan | Paperless Project | Due to Law Concerning Preservation of National Tax Records in Electronic Form, Concur process change will be required. | Syahmi and Nadzrin | Jan, 2022 | 1. Appzen current configuration setting revisit (Jan 7, 2022) 2. Public transporation configuration as a reference point (Jan 7, 2022) 3. Feasibility study whether Appzen can flag it as medium or low risk if the users attach only credit card statement (Jan 7, 2022) | Not Started

## status
In Progress
Complete
Not Started
Overdue
On Hold